## ReadMe - Scope & Assumptions
ELLIPSE REFRESH RUNSHEET - SF EC AS SOURCE (ACUTE-014 / 015 / 001)
Purpose | Defines whether and how the ACUTE-014 (Org), ACUTE-015 (Position) and ACUTE-001 (Employee) interfaces can be used to re-align Ellipse to SuccessFactors EC when Ellipse data is out of sync or inconsistent in a test environment (SIT / UAT), prior to unit test or test-phase entry. SF EC is treated as source of truth.
Design basis | D5-03 ACUTE-001 s2 (Process Flow, Interface Sequencing), D5-03 ACUTE-014 s2.3.3 (Ellipse Table Sequencing) and Process Flow, D5-03 ACUTE-015 s2 (Ellipse Table Sequencing, Process Flow), Ellipse-SF Mapping Specification (File Mechanisms, Index, per-file tabs).
Design position (as signed off) | All three interfaces are DELTA integrations. Extraction uses lastModifiedDateTime on EC OData entities (plus ISC events for ACUTE-001). The initial load explicitly assumes Ellipse is already current - data alignment is a data migration activity, not an interface function. The interfaces route to verb-specific Ellipse operations (Employee.create vs Employee.modify vs transferPosition; MSE875 insert/mod/deletePosition) driven by EC Event / Event Reason. They are NOT idempotent upserts.
Headline answer | The interfaces CAN be used for a CONTROLLED PARTIAL refresh (small, classified drift) by widening the delta window or touch-updating records in EC, provided each record is routed to the correct verb (create vs modify). They CANNOT safely perform a FULL re-baseline: duplicate creates fail in Ellipse (ACUTE-001 test case 6), modifies fail where the record is missing, employee delete is N/A in Ellipse (File Mechanisms), and historical event sequences (transfers, HD, terminations) cannot be replayed from current state. Full re-baseline = data migration reload path, not the interfaces.
Refresh sequence (fixed) | 1. ACUTE-014 Org (MSM010 Table Files #01, MSM80P PRC #02) 2. ACUTE-015 Position (MSM870 files #03-#07 in Ellipse table order MSM870A->B->C..., then MSE875 hierarchy #08/#09) 3. ACUTE-001 Employee (Create #11 + Reference Codes #21, Modify #12, position-dependent files #18-#20). Per ACUTE-001/015: Org before Position before Employee. Interfaces are timer-based and sequential without runtime dependency - for a refresh, enforce hard gating: do not start Position until Org is verified, do not start Employee until Position is verified.
Assumptions | A1: SF EC is source of truth for org, position and employee master data in the target environment. A2: Ellipse environment is a test environment (SIT/UAT) - no production data risk. A3: EC picklists, Event Reasons and mapping elements (Mapping Elements tab) are aligned to the Ellipse target before refresh. A4: Ellipse web service user (CI-47) is provisioned and working in the target environment. A5: Config workbooks are the source of truth for field/config alignment (ACUTE-001 s2.3). A6: No parallel BAU or test activity writes to Ellipse during the refresh window.
Constraints | C1: No employee delete/delimit path in Ellipse via interface - orphaned Ellipse employee records need manual cleanup or reload. C2: Ellipse employee create is sequential screen-service based (high call volume per record) - bulk replay has real throughput and locking implications (CI-11, Paul Yue - lock data while integration pulls back). C3: Refresh sends CURRENT state only - it cannot reconstruct event history (mid-window transfers, HD start/end, rehires). C4: Future-dated records: send one day prior to effective date if Ellipse cannot hold future-dated rows (ACUTE-001/015). C5: Hitachi-side file sequence confirmation still open (CI-12, Christy).
Change control note | A repeatable "full sync / refresh mode" (e.g. iFlow externalised parameter to override the last-run timestamp, plus pre-lookup upsert routing) is NOT in the signed-off design. If the program wants this as a standing capability for SIT/UAT resets, raise it as a CR / future-state recommendation - not a build-phase redesign. The runsheet below works within the current design.
Owner / date | Rajesh Sha, Integration Lead - 3 July 2026. v0.2 draft. Changes from v0.1: (1) source references prefixed by register - OI-n = Open Items tab, CI-n = Clarification Items tab (removes the collision where the two tabs both number from 1); (2) Class C orphaned positions rerouted from #10 deletePosition to the Modify Position path (#09 + #04) per CI-46 (Closed). Working draft for internal review (Andre, Sushant) before circulation.

## Capability Assessment
Interface | Ellipse File # / Name | Ellipse Object / Service | Refresh Use | Supports Refresh? | Notes / Conditions
ACUTE-014 | #01 Table Files (MSM010) | MSM010B - Screen Service | Re-send org structure codes | Yes - conditional | Table code + description updates are re-sendable. Verify existing codes update rather than duplicate; org structure codes in Ellipse must align to EC externalCode/object type (ACUTE-014 s2.3.1).
ACUTE-014 | #02 PRC Codes (MSM80P) | MSM80PB - Screen Service | Re-send PRC hierarchy | Yes - conditional | PRC1-PRC8 hierarchy must be sent in Ellipse table order (ACUTE-014 s2.3.3). Hierarchy deltas require parent rows present first; for refresh, send full hierarchy top-down.
ACUTE-015 | #03 Create Position (MSM870-1) | MSM870A/B - Screen Service | Recreate missing positions | Partial | Only for positions MISSING in Ellipse. Re-sending create for an existing Position ID will error. Requires pre-classification of drift (missing vs stale).
ACUTE-015 | #04 Position Attributes (MSM870-2) | MSM870B - Screen Service | Re-align attributes | Yes - conditional | Modify path suits stale records. Ellipse table sequencing applies: MSM870A before B before dependent tables (ACUTE-015 s2, Table Sequencing).
ACUTE-015 | #05 Position Details (MSM870-5) | MSM8PAA - Screen Service | Re-align details | Yes - conditional | Old technology in Ellipse (File Mechanisms note). Award/rate fields still carry open downstream-impact items (CI-18, 19) - exclude contested fields from refresh scope or accept current mapping.
ACUTE-015 | #06 Position Evaluation (MSM870-8) | MSM8PCA - Screen Service | Re-align evaluation | Yes - conditional | CI-21 (evaluation date/reason downstream impact) unresolved - same treatment as #05.
ACUTE-015 | #07 Position Costing (MSM870-7) | MSM8PUA - Screen Service | Re-align costing | Yes - conditional | Costing logic update pending Christy feedback (CI-22). Confirm logic version before refresh.
ACUTE-015 | #08 Insert Position (MSE875) | PosnHierarchy.insertPosition | Rebuild hierarchy for missing links | Partial | Insert only where hierarchy link missing. Parent (FL) position must exist first - process top-down by hierarchy level.
ACUTE-015 | #09 Modify Position (MSE875) | PosnHierarchy.modPosition | Re-point reporting lines | Yes - conditional | Also sent on parent position update (File Mechanisms query, Christy checking #09 on parent update). Safe for re-pointing existing links.
ACUTE-015 | #10 Delete Position (MSE875) | PosnHierarchy.deletePosition | Remove orphaned positions (via #09/#04) | Conditional - not via #10 | CI-46 CLOSED: position removal is managed as part of Modify Position, not deletePosition. Route orphaned positions via #09 (map Superior ID as DeletedCOR) + #04 (Position Attributes - Occupancy Status = D), per File Mechanisms. #10 deletePosition is not the sanctioned path; obtain business confirmation per orphan before delimiting.
ACUTE-001 | #11 Create Employee (MSE81S) | Employee.create | Recreate missing employees | Partial | Missing-in-Ellipse records only. Duplicate create returns Ellipse error (ACUTE-001 test case 6) - no upsert. High call volume per record (sequential screen services) - throttle batch size and window.
ACUTE-001 | #12 Modify Employee (MSE81S) | Employee.modify | Re-align stale employee data | Yes - conditional | Best-fit refresh verb for existing records. Trigger via touch-update in EC or widened delta window. Sends current state; does not replay history.
ACUTE-001 | #13 Transfer Employee (MSE81S) | Employee.transferPosition | Correct position assignment | Caution | Event-reason driven (JOBPERM, PROPNP, TRANSECI/O). A refresh is not an event - transfers mid-drift-window cannot be replayed; only end-state can be forced via a corrective transfer with an agreed event reason. Needs functional (Gary) agreement per case.
ACUTE-001 | #14 Terminate Employee (MSE81S) | Employee.transferPosition | Re-apply missed terminations | Caution | Termination date = actual last date in Ellipse (CI-2). Re-apply only classified missed terminations; verify term reason mapping.
ACUTE-001 | #15 Reactivate Employee (MSE81S) | Employee.transferPosition | Rehire / deletion of termination | No - hold | Rehire design pends formal business decision (OI-5, Ehsan/Gary; G-12 uncosted). Exclude rehire scenarios from refresh scope until decided.
ACUTE-001 | #16 Suspend Employee (MSE81S) | Employee.transferPosition | n/a | No | Suspension confirmed not required (CI-6, Patrick) - handled via LWOP. Not part of refresh.
ACUTE-001 | #17 Physical Location Trf (MSO829) | MSM829 - Screen Service | n/a | No | No longer required - field defaulted (Index / File Mechanisms).
ACUTE-001 | #18-#20 Emp Position (MSE81S WS) | Create/Modify/Delete Emp Position | Re-align Higher Duties | Caution | HD modify covers end-date change only; other changes need delete + recreate (Index note). HD deletion downstream behaviour still open (File Mechanisms). Handle HD drift case-by-case.
ACUTE-001 | #21 Reference Codes (MSE81S_RC) | Screen Service | Contractor (CW) additional info | Yes - conditional | Sent with create for contractors. Include when recreating CW records.
ALL | Delete / delimit employees | n/a | Remove orphaned Ellipse employees | No | File Mechanisms: Delete/Delimit = "NA in Ellipse" for employees. Orphans require manual Ellipse correction or environment reload - flag in reconciliation output.

## Refresh Runsheet
# | Phase | Task | System / Artefact | Owner | Entry Criteria | Exit Criteria / Evidence | Status
1 | 0. Freeze & Baseline | Declare refresh window; freeze EC data entry and stop all ACUTE-014/015/001 iFlow schedules in the target tenant/environment pair | SAP IS schedules; EC test tenant | Rajesh / Andre | Drift confirmed; window agreed with test team (Sushant) | Schedules undeployed/paused; freeze notice issued | Not Started
2 | 0. Freeze & Baseline | Snapshot Ellipse target environment (DB backup or restore point) so the refresh is reversible | Ellipse (Hitachi/Infra) | Andre / Paul Yue | Freeze in place | Restore point reference recorded | Not Started
3 | 0. Freeze & Baseline | Confirm Ellipse web service user works in target environment (create/modify/transfer test call) | Ellipse MSE81S / MSM870 | Shashank / Malkit | CI-47 resolved for this environment | Successful test call logged in SAP IS monitoring | Not Started
4 | 0. Freeze & Baseline | Confirm mapping elements, picklists and event reason mappings deployed match Mapping Spec version in use | Mapping Spec; value mappings in SAP IS | Saahhil / Brian | Mapping Spec version agreed | Value mapping version noted; mismatches logged | Not Started
5 | 1. Reconcile | Extract SF EC current-state: org objects, positions, employees (OData full pull, keyed on externalCode / Position ID / personIdExternal+userId) | EC OData (PerPerson, EmpJob, EmpEmployment, Position, FO) | Saahhil / Gurdeep | Freeze in place | Extract files timestamped and stored | Not Started
6 | 1. Reconcile | Extract Ellipse current-state for same objects (MSM010/MSM80P, MSM870x, MSE875, MSE81S views) | Ellipse extracts (Hitachi) | Christy / Hitachi | Freeze in place | Extract files timestamped and stored | Not Started
7 | 1. Reconcile | Compare and classify drift per record: A) missing in Ellipse B) stale in Ellipse C) orphaned in Ellipse D) event-history drift (transfer/term/HD missed) | Reconciliation workbook | Rajesh / Saahhil | Both extracts complete | Classified drift register with counts per class | Not Started
8 | 2. Decide Path | Decision gate: if drift is small and classifiable (A/B dominant) -> interface replay per this runsheet. If drift is structural, large, or class C/D heavy -> data migration reload of Ellipse (not interfaces). Record decision | Drift register; this workbook | Rajesh w/ Andre, Sushant | Drift register complete | Decision recorded with rationale; Eshan informed if schedule impact | Not Started
9 | 2. Decide Path | Scope exclusions confirmed: rehire (OI-5), suspension, physical location, contested position fields (CI-18/19/21/22) | ReadMe tab; Open Items | Rajesh / Gary | Decision = interface replay | Exclusion list appended to drift register | Not Started
10 | 3. Org Refresh (ACUTE-014) | Replay org drift: re-send Table Files (#01) then PRC codes (#02) top-down through PRC hierarchy. Trigger via touch-update in EC or widened lastModifiedDateTime window on a manual run | SAP IS ACUTE-014 iFlow (manual run) | Gurdeep / Brian | Phase 2 complete; Ellipse locked for other writes (CI-11) | All org messages successful in message monitoring; failures triaged | Not Started
11 | 3. Org Refresh (ACUTE-014) | Verify org alignment: re-extract MSM010/MSM80P and diff against EC extract | Reconciliation workbook | Saahhil | Replay complete | Zero unexplained org variances - HARD GATE for Phase 4 | Not Started
12 | 4. Position Refresh (ACUTE-015) | Class A (missing): create positions via #03 then attributes/details/eval/costing #04-#07 in Ellipse table order, then hierarchy insert #08 top-down by level | SAP IS ACUTE-015 iFlow (manual run) | Gurdeep / Brian | Org gate passed | Create messages successful; per-record log | Not Started
13 | 4. Position Refresh (ACUTE-015) | Class B (stale): modify attributes #04-#07 and re-point hierarchy via #09 | SAP IS ACUTE-015 iFlow | Gurdeep / Brian | Class A complete | Modify messages successful | Not Started
14 | 4. Position Refresh (ACUTE-015) | Class C (orphaned positions): remove via the Modify Position path - send #09 (map Superior ID as DeletedCOR) + #04 (Occupancy Status = D) per File Mechanisms / CI-46 (Closed: delete managed as part of Modify Position). #10 deletePosition is not the sanctioned route; obtain business confirmation per orphan before delimiting, else log and leave | Ellipse MSM870 #04 + MSE875 #09 | Christy / business | Orphan list from drift register | Disposition recorded per orphan | Not Started
15 | 4. Position Refresh (ACUTE-015) | Verify position alignment: re-extract and diff. HARD GATE for Phase 5 | Reconciliation workbook | Saahhil | Replays complete | Zero unexplained position variances | Not Started
16 | 5. Employee Refresh (ACUTE-001) | Class A (missing): Employee.create #11 (+ Reference Codes #21 for CWs). Throttle batch size - sequential screen services drive high call volume per record; agree batch/window with Hitachi | SAP IS ACUTE-001 iFlow (manual run) | Gurdeep / Shashank | Position gate passed | Creates successful; throughput within agreed limits | Not Started
17 | 5. Employee Refresh (ACUTE-001) | Class B (stale): Employee.modify #12 via touch-update or widened delta window - current state only | SAP IS ACUTE-001 iFlow | Gurdeep / Shashank | Class A complete | Modifies successful | Not Started
18 | 5. Employee Refresh (ACUTE-001) | Class D (event-history drift): corrective transfer #13 / termination #14 case-by-case with agreed event reasons; HD via #18-#20 noting modify=end-date-only. Rehire cases parked (OI-5) | SAP IS ACUTE-001 iFlow; Gary for event reasons | Rajesh / Gary | Case list agreed | Each case actioned or parked with reason | Not Started
19 | 5. Employee Refresh (ACUTE-001) | Class C (orphaned employees): no interface delete path - manual Ellipse correction list to business/Hitachi | Ellipse manual | Christy / business | Orphan list | Disposition recorded per orphan | Not Started
20 | 6. Verify & Release | Full re-reconciliation across org, position, employee; publish variance report (target: zero unexplained) | Reconciliation workbook | Saahhil / Rajesh | Phases 3-5 complete | Variance report issued | Not Started
21 | 6. Verify & Release | Reset iFlow last-run timestamps to refresh completion time; re-deploy schedules in agreed order (014 -> 015 -> 001) | SAP IS | Gurdeep | Variance report accepted | Schedules live; first delta runs clean in monitoring | Not Started
22 | 6. Verify & Release | Lift freeze; hand environment to test team with refresh completion note and known exclusions | Email / test entry checklist | Rajesh -> Sushant, Andre | Schedules live | Environment released; unit test / SIT entry can proceed | Not Started

## Risks & Dependencies
# | Risk / Dependency | Source Reference | Impact on Refresh | Mitigation / Action | Owner
1 | Interfaces are not idempotent - duplicate create errors, modify-on-missing fails | ACUTE-001 test case 6; File Mechanisms verb routing | Blind replay corrupts run results and floods error handling / ServiceNow ticketing | Mandatory drift classification (Phase 1) before any replay; route per class to correct verb | Rajesh / Saahhil
2 | No employee delete path in Ellipse via interface | File Mechanisms - Delete/Delimit NA for employee | Orphaned Ellipse employees persist after refresh; test results skewed | Orphan disposition list to business/Hitachi for manual correction; document residuals in release note | Christy
3 | Refresh sends current state only - event history not replayable | ACUTE-001 s2 (event/event-reason driven) | Transfers, terminations, HD start/end that occurred during drift window cannot be reconstructed | Class D handled case-by-case with Gary agreeing corrective event reasons; park rehire pending OI-5 | Rajesh / Gary
4 | Ellipse throughput and locking under bulk replay | Sequential screen services (12 screens, up to ~54 calls/record); CI-11 (Paul Yue - lock data during pull-back) | Long run windows; contention with any parallel activity; partial failures mid-batch | Agree batch sizes and run window with Hitachi; exclusive access during refresh; retry policy per ACUTE-001 s on error handling | Andre / Paul Yue
5 | Hitachi-side file sequence not formally confirmed | CI-12 (Christy checking internal Hitachi sequence) | Wrong intra-interface file order can fail dependent table loads | Confirm before Phase 3; interim: follow Ellipse Table Sequencing sections in 014/015 and File Mechanisms order | Christy
6 | Contested position fields (award/rates, evaluation, costing) unresolved | CI-18, 19, 21, 22 | Refreshing these fields may propagate wrong values downstream | Exclude from refresh scope or accept current mapping explicitly at Phase 2 decision gate | Rajesh / business
7 | Rehire design undecided | OI-5 (Ehsan/Gary); G-12 uncosted | Rehire drift cases cannot be actioned | Park with named list; revisit after formal decision | Ehsan / Gary
8 | Web service user / environment access | CI-47 (Shashank/Malkit build blocker) | Refresh cannot execute in target environment | Phase 0 verification task; escalate to Andre if unresolved | Andre
9 | Standing refresh capability is out of signed-off design | ACUTE-001/014/015 - initial load assumes Ellipse current | Repeated ad-hoc refreshes without governance erode design baseline | If SIT/UAT resets will recur, raise CR for a parameterised full-sync mode (timestamp override + pre-lookup create/modify routing) as future-state | Rajesh -> Eshan